## Dashboard
Field | Value
Event | Harbor Lights Community Gala 2027 / 海港燈火社區慈善晚宴 2027
Date | 2027-05-15 (Saturday, May 15, 2027)
Time | 6:00 PM – 9:30 PM
Venue | Harbor Lights Community Hall, 88 Wharf Street, New Haven, CT
Website | https://harborlights.example.org
Contact | gala@harborlights.example.org
Tickets | Individual $150 · Student/Senior $60 · Harbor Table (10 seats) $1,500

## Guest List
Name | Category | Intro | DRI | Location | Role | Status | Email
Dr. Grace Wong 黃慧君 | Keynote | — | Joanne | New Haven | Keynote speaker | Waiting | grace.wong@elmcitykids.example.org
Lily Chan 陳麗莉 | Honoree | Raymond Tse (knows her personally) | Ivy | New Haven | Community Service Honoree | Confirmed | lily@elmcityyouth.example.org
Raymond Tse 謝國華 | Board | — | Eric | Hamden | Board member / intermediary | Confirmed | raymond.tse@harborlights.example.org
C.K. Lee 李志強 | Sponsor | — | Eric | New Haven | Owner, Golden Phoenix Restaurant | Confirmed | ck@goldenphoenix.example.com
Michael O'Brien | Media | — | Joanne | West Haven | MC | Waiting | mobrien@whbr.example.org
黃偉霖教授 (黃老師) | Guest of honor | Raymond Tse | Ivy | New Haven | Toast | Waiting | weilin.huang@faculty.example.edu

## outreach log
Name | Channel | Handle / Contact | Log
Dr. Grace Wong | Email; letter | grace.wong@elmcitykids.example.org | 9/24 emailed; 10/5 mailed zh-Hant invitation letter; pending
Lily Chan | Phone (via Raymond) | via Raymond Tse | 10/1 passed message via Raymond Tse; 10/9 Raymond: 'she said yes'
Michael O'Brien | Instagram | IG @mike.whbr.example | 10/7 IG DM, pending
Prof. Weilin Huang | Email (via Raymond) | weilin.huang@faculty.example.edu | 10/10 Raymond forwarded invitation; pending
Pacific Harbor Credit Union | Email | community@pacificharborcu.example.org | 9/30 sent sponsorship package; 10/8 asked for invoice for Lighthouse tier, pending board OK

## Sponsorship
Sponsor | Tier | Amount (USD) | Owner | Status | Notes
Pacific Harbor Credit Union | Lighthouse | 5000 | Eric | Pending
Golden Phoenix Restaurant | In-kind | 0 | Eric | Confirmed | Dinner for 200 (C.K. Lee)
Elm Street Pharmacy | Friend | 500 | Eric | Confirmed